## RACI Matrix Legends
Zomato - Restaurant Market Expansion Intelligence
Business Layer RACI Matrix | Stackholder Roles
R = Responsible | Role | Meaning
A = Accountable | ES | Executive Sponsor / Business Head
C = Consulted | GL | Growth / Expansion Lead
I = Informed | PL | Restaurant Partnerships Head
| CM | City / Market Manager
| CSL | Category Strategy Lead
| BL | BI / Analytics Lead
| BA | Business Analyst
| DA | Data Analyst
| PSL | Product Strategy Lead
| ROM | Restaurant Operations / Merchant Ops Manager

## RACI Matrix
Business Layer Activity / Deliverable | ES | GL | PL | CM | CSL | BL | BA | DA | PSL | ROM
Project vision and business objective definition | A | R | C | I | C | I | R | I | C | I
Problem statement finalization | A | R | C | C | C | I | R | I | C | I
Stakeholder identification and mapping | I | C | C | C | C | I | R | I | I | I
KPI tree design | A | R | C | C | R | C | R | C | C | I
BRD creation | I | C | C | I | C | C | A/R | C | I | I
FRD creation | I | C | C | I | C | C | A | R | C | I
User stories definition | I | C | C | I | C | I | A/R | C | I | I
RACI matrix preparation | I | C | C | C | C | I | A/R | I | I | I
As-Is process mapping | I | C | R | R | C | I | A | C | I | C
To-Be process mapping | A | R | C | C | C | C | R | C | C | C
Business rules definition | I | C | C | C | R | C | A/R | C | I | I
Gap analysis | I | R | C | C | C | C | A/R | C | C | I
Expansion scoring logic definition | A | R | C | C | R | C | R | C | C | I
Dashboard requirement specification | I | C | C | C | C | A | R | C | C | I
Executive summary / business recommendations | A | R | C | C | C | C | R | C | C | I
Data quality issue review (business side) | I | C | C | C | C | C | R | A/R | I | C
Final business sign-off | A | R | C | C | C | C | R | I | C | I

## RACI View
Deliverable | ES | GL | PL | CM | CSL | BL | BA | DA | PSL | ROM
Problem Statement | A | R | C | C | C | I | R | I | C | I
Stakeholder Map | I | C | C | C | C | I | A/R | I | I | I
KPI Tree | A | R | C | C | R | C | R | C | C | I
BRD | I | C | C | I | C | C | A/R | C | I | I
FRD | I | C | C | I | C | C | A | R | C | I
User Stories | I | C | C | I | C | I | A/R | C | I | I
RACI Matrix | I | C | C | C | C | I | A/R | I | I | I
As-Is Process Map | I | C | R | R | C | I | A | C | I | C
To-Be Process Map | A | R | C | C | C | C | R | C | C | C
Gap Analysis | I | R | C | C | C | C | A/R | C | C | I
Executive Summary | A | R | C | C | C | C | R | C | C | I